## Sheet1
Smart Appointment Booking System | [6 empty] | Project Summary: The Smart Appointment Booking System is a web-based application that allows clients to book,modify, and cancel appointments online. The system also enables administrators to configure schedules and manage staff availability. Staff members can view their daily and weekly schedules. |  |  |  | FUTURE ENHANCEMENTS: AI-based booking recommendation system
Project Goal : this system will replace manual, error-prone processes with a real-time digital solution. Built with scalability and user experience at its core
Group Members
|  | Developer Name |  | Roles
| 1 | Ahed Akrout |  | Team Leader - Backend
| 2 | Melad Mustafabadran |  | Frontend
| 3 | Beste Ozkan |  | Designer
| 4 | Osamah Naji |  | Tester
| Project Progress | [6 empty] | Resources |  | Risk Managment
|  | Mission | Responsible |  | Deadline | Status / Date |  | Product | Total Budget | Early testing to reduce integration problems
| 1 | Project Requirements Analysis | Ahed - Melad |  | 2026-02-25 | In Progress |  | Domain | 20$ | Version control to prevent code loss
| 2 | UI/UX Design | Beste |  | 2026-03-01 | In Progress |  | Host | 720 | Backup database strategy
| 3 | Website Pages Development | Melad |  | 2026-03-20 | To Do |  | Total Team Salary | 35350$ | Weekly monitoring to avoid delays
| 4 | Backend API Development | Ahed |  | 2026-04-10 | To Do |  | Total Budget: | 36090$
| 5 | Database Implementation | Ahed |  | 2026-04-20 | To Do
| 6 | System Testing | Osamah |  | 2026-04-25 | To Do |  | Task | Daily Budget
| 7 | Bug Fixing | Melad - Ahed |  | 2026-05-01 | To Do |  | Front End Developer | 350$
| 8 | Documentation | All Members |  | 2026-05-05 | To Do |  | Back End Developer | 340$
[8 empty] | UI/UX Designer | 280$
[8 empty] | Tester | 280$
Note on P16: Melad Mustafabadran: Not Needed Yet