## Intro
Smart Appointment Booking System | [6 empty] | Project Summary: The Smart Appointment Booking System is a web-based application that allows clients to book,modify, and cancel appointments online. The system also enables administrators to configure schedules and manage staff availability. Staff members can view their daily and weekly schedules. |  |  | FUTURE ENHANCEMENTS: AI-based booking recommendation system
Project Goal : this system will replace manual, error-prone processes with a real-time digital solution. Built with scalability and user experience at its core
Group Members
|  | Developer Name |  | Roles
| 1 | Melad Mustafabadran |  | Team Leader - Frontend
| 2 | Beste Ozkan |  | Designer - Frontend
| 3 | Ahed Akrout |  | Backend
| 4 | Osamah Naji |  | Tester
| Project Progress | [6 empty] | Resources
|  | Mission | Responsible |  | Deadline | Status / Date |  | Product | Budget
| 1 | Project Requirements Analysis | Melad - Ahed |  | 2026-02-25 | Done |  | Domain
| 2 | UI/UX Design | Beste |  | 2026-03-01 | Done |  | Host
| 3 | Website Pages Development | Melad |  | 2026-03-20 | Done
| 4 | Backend API Development | Ahed |  | 2026-04-10 | Done
| 5 | Database Implementation | Ahed |  | 2026-04-20 | Done
| 6 | System Testing | Osamah |  | 2026-04-25 | Done |  | Total Budget: | 0$
| 7 | Bug Fixing | Melad - Ahed |  | 2026-05-01 | Done
| 8 | Documentation | All Members |  | 2026-05-05 | Done
Status updated: 2026-04-30
Note on P16: Melad Mustafabadran: Not Needed Yet

## Risks and Security
Smart Appointment Booking System
ID | Risk Identification | [5 empty] | Risk Mitigation | Code Security and Data Privacy
R-0 | Double Booking Problem | [5 empty] | 1.Prevent Double Booking | Role-Based Authorization
| The system allows users to book time slots so two users might reserve the same appointment slot at the same time. | [5 empty] | The system will check if the selected time slot already exists in the database before confirming a new appointment. | The system will define different user roles model ensures that users only access functions allowed by their role.
R-1 | Backend Development Complexity | [5 empty] | 2.Database Backup | Authentication Security
| The appointment scheduling logic requires checking available time slots, updating the database, and preventing conflicts. | [5 empty] | Regular backups will be scheduled to prevent data loss in case of system failure. | Users must create an account and log in before accessing booking features. The system will use encrypted password
| If the backend logic is not designed correctly it may cause system errors or incorrect bookings. | [5 empty] | appointment records may be lost. | Data Privacy Protection:
R-2 | Database Data Loss | [5 empty] | 3.Secure Authentication | 1.The system will store only essential data: 1.Name 2.Email 3.Appointment details
| The system stores user accounts and appointment data. If the database fails or is not backed up properly, appointment records may be lost. | [5 empty] | The system will require users to log in before booking appointments. Passwords will be stored using encryption methods. | 2.Sensitive information such as passwords will be stored using encryption.
R-3 | Unauthorized Access | [6 empty] | 3.Access to the database will be restricted to the backend server to prevent unauthorized access.
If authentication and role management are not implemented correctly, unauthorized users may access admin or staff functions.
R-4 | Security Vulnerabilities
Security issues also have a high impact because they may expose sensitive user data.
R-5 | Notification Failure
If email or SMS notification services fail, users may not receive appointment confirmations or reminders.
R-6 | User Input Errors
Users may enter incorrect information when booking appointments, which could lead to scheduling confusion.
R-7 | Data Privacy Risk
User personal information such as names, phone numbers, and emails must be protected.
R-8 | Performance Issues
If many users access the system at the same time, the system may become slow or unresponsive, especially during peak booking times.
Risk Assessment and Management
|  | ID | Risk | Probability | Impact | Risk Level
|  | R-0 | Double booking bug | Medium | High | High
|  | R-1 | Backend logic errors | Medium | High | High
|  | R-2 | Database data loss | Low | Medium | Medium
|  | R-3 | Unauthorized system access | Medium | High | High
|  | R-4 | Security Vulnerabilities | Medium | High | High
|  | R-5 | Notification Failure | Medium | Medium | Medium
|  | R-6 | User Input Errors | High | Medium | High
|  | R-7 | Data Privacy Risk | Low | High | Medium
|  | R-8 | Performance Issues | Medium | High | High

## Validation and Testing Plan
Smart Appointment Booking System
Implementation Roadmap |  |  |  |  | Validation Plan
The system will be validated by simulating real user actions such as account registration, login, appointment
| Mission | Responsible | Deadline | Status / Date | booking, and appointment cancellation.
1 | Project Requirements Analysis | Melad - Ahed | 2026-02-25 | Done | Test cases will be executed to confirm that the system correctly processes booking requests and stores
2 | UI/UX Design | Beste | 2026-03-01 | Done | appointment data in the database.
3 | Website Pages Development | Melad | 2026-03-20 | Done | The system will be validated to ensure that already reserved time slots cannot be booked again.
4 | Backend API Development | Ahed | 2026-04-10 | Done | User roles will be validated to confirm that users, staff, and administrators can only access features assigned
5 | Database Implementation | Ahed | 2026-04-20 | Done | to their permissions.
6 | System Testing | Osamah | 2026-04-25 | Done | Data validation will ensure that incorrect or incomplete input data is rejected by the system.
7 | Bug Fixing | Melad - Ahed | 2026-05-01 | Done
8 | Documentation | All Members | 2026-05-05 | Done | Testing Plan
Unit testing will be performed on individual modules such as registration, login, booking.
Integration testing will verify communication between frontend interface, Python backend, and database system.
System testing will evaluate the complete workflow from user registration to appointment scheduling and
management.
Success Criteria |  |  |  |  | Performance testing will measure system stability when multiple users attempt to access the booking system
1 | The registration and login processes must operate without errors and correctly store user information in the database. |  |  |  | simultaneously.
2 | The system must correctly store booking information and display confirmation messages after successful reservations. |  |  |  | Security testing will verify that authentication mechanisms and data protection measures prevent
3 | If a time slot has already been reserved, the system must reject the request and notify the user that the slot is unavailable |  |  |  | unauthorized access.
4 | Users must be able to cancel or modify their appointments, and staff must be able to view and manage scheduled appointments.
5 | The system must correctly enforce role permissions
6 | The system maintains secure user authentication.
7 | The platform performs reliably under multiple user requests.
8 | The project is completed within the 8-week development timeline.